## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 142
Days In Sprint:
Burndown Chart
User Stories |  | Days (Points Completed) | [5 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | Task Balance | Percentage Completed
User will be able read current news on the home page so that I stay current on BBC news. | 36 | 2 | 12 | 12 | 3 | 3 | 4 | 0 | 100%
User will be able see the weather in my current area and forecasting of the weather. | 34 | 7 | 10 | 7 | 4 | 4 | 2 | 0 | 100%
User will be able see different events and schedule of television programs. | 20 | 6 | 6 | 5 | 2 | 0 | 0 | 1 | 95%
User will be able to comment about article so that others can read them. | 16 | 0 | 0 | 4 | 6 | 2 | 4 | 0 | 100%
User will be able to read old news that is no longer on the home page, so I can access things I remember from the past or that others mention to me. | 20 | 5 | 6 | 9 | 0 | 0 | 0 | 0 | 100%
I can include a teaser with each article so that site visitors can decide if they want to read the rest. The teaser shows up on the front page for all to read. | 16 | 0 | 0 | 0 | 7 | 5 | 4 | 0 | 100%
Effort Remaining | 142 | 122 | 88 | 51 | 29 | 15 | 1 | 1 | 99.3%
Ideal Trend | 142 | 134.9 | 127.8 | 120.7 | 113.6 | 106.5 | 99.4
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days